A SERIES PLANNING TIME LINE

Before the Start of a Series

- 4-10 months out – Series Idea/Title (Teaching Team)

- 1 month out – Message Titles and Series Themes Set (Teaching Team)

- 1 month out –Begin collecting creative elements for series based on message titles and themes

- 3 weeks out – Creative Planning Meeting – creative ideas for the series shared and organized

- 10 days out – Series Specific Staging/Props ready for testing

Series Begins