A SUNDAY PLANNING TIME LINE

Before a Specific Sunday

- 3 weeks out – Message Research Team Research Due

- 2 weeks out – Specific Music and Creative Elements Planned

- 2 weeks out – 1st Draft of Message Notes from Teaching Pastor in Worship Planning Meeting

- 2 weeks out – 1st Draft of Worship Order in Worship Planning Meeting

- 5 days out – Final Draft of Message Notes from Teaching Pastor in Worship Planning Meeting

- 5 days out – Final Draft of Worship Order and Creative Elements in Worship Planning Meeting; Specific prayer time for service

- 3 days out – Production Meeting Finalizing Worship Order and Elements of Service

- 3 days out – finalize message manuscript completed; trial run of message

- 3 days out – Thursday Midnight Rule – everything finalized for Sunday

Sunday Service conducted